## Sheet1
Technical safety abbreviation
[6 empty] | IFR | [6 empty] | IFA | [6 empty] | IFC |  |  | REMARKS
CONTRATOR's Doc No | DOC Title |  |  |  | START | IFR Date |  | TR NO | Date Sent | Rev Sta | Issue For | Date Sent | IFA |  | TR No | Date Sent | Rev Sta | Issue For | Next Rev | IFC Date |  | TR No
|  |  | Status | Definition |  | Planned | Actual | [5 empty] | Planned | Actual | [5 empty] | Planned | Actual
| Project Management & Administration | Hours
| Kick-off Meeting | 20
| Site visit report | 4
| Project Basis of design | 24
| Project Schedule | 72
| Project Execution Plan | 40
| Project Quality Plan | 56
| Construction Scope of Work | 40
| Project Management Plan | 20
| HSE Plan | 52
| Master Deliverables Register and Progress Measurement System | 68
| Weekly Progress/Management Meetings | 60
| Regular discipline engineer meetings | 60
| Input to other Discipline | 66
| Project Administration | 168
| Project Control Procedure | 34
| Document Control Plan | 34
| HAZOP/HAZID Review | 16
| Design Review Report | 32
| Monthly Report | 36
| Project Close-Out Report | 44
| Total | 946
| Technical Safety | Hours
| HAZOP Terms of Reference | 32
| HAZOP Close Out Report | 76
| HAZID Terms Of Reference | 32
| HAZID Close Out Report | 56
| HAZOP Study Report | 56
| HAZID Study Report | 52
| HSE Design Philosophy | 72
| Hazardous Area Classification Schedule | 74
| Hazardous Area Classification Drawings | 104
| Kick Off meeting | 6
| Safety Workshops (HAZID, HAZOP) and design review | 80
| Weekly Discipline Meetings | 24
| Project Weekly Meeting | 24
| Total | 688
| Process | Hours
| Flow Assurance - Slugging Transient Analysis and Report | 172
| HYSYS Simulation & Report | 64
| Heat & Material Balance Report | 34
| Line Sizing Calculation Note | 44
| Equipment Sizing Calculation Note | 92
| Utility Balance Report | 64
| Line List | 58
| GHG Emission Report | 56
| Process Operating and Control Philosophy -Update | 52
| Isolation Philosophy - Update | 20
| Control Valve Sizing Calculation Note | 60
| Equipment Selection report | 88
| Process Datasheet (4 nos) | 88
| Flare system analysis Report (PSV, Flare Hydraulics, etc) | 128
| Process Flow Diagram (1 Nos) - Existing | 56
| P&ID - (3 Nos) - Existing | 80
| P&ID - (3 Nos) - New (new equipments) | 88
| P&ID - Vent Header tie-in | 48
| P&ID - Closed & Open Drain tie-in | 48
| UP&ID - Flare Header Demo | 32
| UP&ID - Closed & Open Drain header Demo | 32
| Input to Cause and Effect Matrix | 42
| Process & Flow Assurance Basis of Design | 44
| P&ID - (3 Nos) - Existing Demo | 32
| UFD - Update (2 Nos) | 20
| Input to multi-disciplinary equipment selection study. | 24
| Update to Alarm and Trip Settings | 56
| Project Meeting | 12
| HAZOP, HAZID and Other design review | 40
| Site Visit and input to site visit report | 40
| Liquid drop out mitigation strategy report | 96
| Weekly Discipline Meetings | 24
| Project Weekly Meeting | 24
| Total | 1858
| Instrumentation | Hours
| Instrument I/O List | 68
| Instrument Index/List | 104
| Instrument Cable Schedule | 16
| Instrumentation, Control and Automation Philosophy | 88
| General Instrument Specification | 80
| Instrument Datasheet (Flow, Level, Pressure, Temperature, SDV, PSV, Control Valve etc) | 180
| Instrument Cause & Effect Matrix | 104
| Instrument MTO (Priced and Unpriced) | 80
| Instrument Location Layout | 152
| Instrument Cable Tray Routing Layout | 56
| Instrument Hook-Up Drawing/Details | 152
| Instrument Loop Drawing | 64
| Instrument Junction Box Wiring Diagram | 74
| Control System Architectural Diagram (Update) | 152
| Project Meeting | 12
| HAZOP, HAZID and Other Design Review | 40
| Site Visit and Input to Site Visit Report | 24
| Input to other disciplines | 48
| Preliminary Sizing Calculation (Actuator) | 68
| Total | 1562
| Piping | Hours
| Piping Material Specification | 84
| Piping Design Basis | 84
| Standard Pipe Support Specification | 64
| Piping Tie-in List | 40
| Manual Valve List | 40
| Manual Valve Datasheets | 48
| Piping Specialty Item List | 64
| Specialty Items Datasheets | 86
| Piping MTO | 104
| Layout Review Report | 64
| Equipment Location Plan | 76
| Piping Demolition Drawing | 84
| Overall Key Plan for Piping General Arrangment | 140
| Piping General Arrangment Drawing-Inlet Gas Scrubber Area | 148
| Piping General Arrangment Drawing-Heater Area | 148
| Pipe Support Location Drawing-Inlet Gas Scrubber Area | 84
| Pipe Support Location Drawing-Heater Area | 84
| Piping Isometric Drawings | 194
| Input to Basis of Design | 24
| Input to other Discipline Deliverables | 40
| Project Meeting | 12
| HAZOP, HAZID and Other design review | 40
| Site Visit and input to site visit report | 60
| Review of Client Documentation | 28
| Total | 1840
| Mechanical | Hours
| Audit | 20
| Constructability Review Report | 26
| Input to other Discipline deliverables | 36
| Progress Meetings/Report | 12
| Technical Design Review | 16
| Site Visit / Site Visit Report | 28
| HAZOP Review | 8
| QAQC audit | 6
| Specifications for all new equipment | 48
| Sizing Calculation for Inlet Gas Scrubber | 24
| Sizing Calculation for Slop Tank | 24
| Data Sheet for Inlet Gas Scrubber | 28
| Data Sheet for Slop Tank (To be confirmed if Required) | 28
| Data Sheet for Gas (Fired) Heater | 28
Technical Bid Evaluation for Inlet Gas Scrubber
Technical Bid Evaluation for Slop Tank
Technical Bid Evaluation for Gas (Fired) Heater
| Requisition for Inlet Gas Scrubber | 64
| Requisition for Quotation for Slop Tank (To be confirmed if Required) | 64
| Requisition for Quotation for Gas (Fired) Heater | 64
| General Arrangement Drawing for Inlet Gas Scrubber | 120
| General Arrangement Drawing for Slop Tank (To be confirmed if Required) | 120
| General Arrangement Drawing for Gas (Fired) Heater | 120
| Preparation of LLI List | 20
| Kick Off Meeting | 4
| Material Selection Report | 60
| Material Selection Diagram | 72
| Painting Specification | 40
| Welding specification | 40
| NDE Specification | 40
| Specification for Insulating Flange and Kits | 40
| Total | 1200
| Civil/Structural | Hours
| Review of Geotechnical Survey (to be provided by Company) | 16
| Review of Topographical Survey (to be provided by Company) | 16
| Civil-Structural Basis of Design | 72
| Specification of Steel Works | 72
| Specification for Foundation | 72
| Specification for Concrete Works | 72
| Equipment Foundation (Heater, Scrubber and Slop Tank) Design Report | 128
| Specification for Site Preparation and Earthworks | 72
| Bearing Capacity Calculation Report | 56
| Pipe Support and Foundation Design Report | 68
| Drainage Calculation Report | 68
| Pavement Design Report | 68
| MTO | 56
| Civil Site Layout (Update to Existing assumed) | 72
| Drainage Layout and Details (Update to Existing assumed) | 72
| Pavement Layout and Details (Update to Existing assumed) | 72
| Scrubber Foundation Plan, Sections and Details | 76
| Heater Foundation Plan, Sections and Details | 76
| Slop Tank Foundation Plan, Sections and Details | 76
| General Foundation Layout | 76
| Bar bending schedule | 52
| Input to MDR | 8
| Audit | 20
| Constructability Review Report | 48
| Input to other Discipline deliverables | 36
| Progress Meetings/Report | 16
| Technical Design Review | 32
| Site Visit / Site Visit Report | 40
| QAQC audit | 6
| Total | 1614
| Electrical | Hours
| Electrical Design Philosophy | 65
| Lightning Protection, Earthing and Bonding Philosophy | 65
| Lighting Philosophy | 65
| Cable specification | 65
| Data sheet for cables | 64
| Illumination calculation | 90
| Cable sizing calculation | 65
| Electrical MTO | 65
| Cable Routing layout | 80
| Cable tray layout | 80
| Lighting layout Drawing | 80
| Earthing layout | 72
| Project Meeting | 12
| HAZOP, HAZID and Other design review | 40
| Site Visit Report | 24
| Hazardous Area Schedule | 130
| Hazardous Area Layout | 100
| Weekly Discipline Meetings | 24
| Project Weekly Meeting | 24
| Total | 1210
| Corrosion | Hours
| Input to Site Visit | 0
| Material Selection Report | 0
| Material Selection Diagram | 0
| Painting Specification | 0
| Welding specification | 0
| NDE Specification | 0
| Specification for Insulating Flange and Kits | 0
| Total | 0
| Total Man-Hours | 10918
Note on I116: Olaniyi Afolabi: Piping GAD for the Metering and Regulating Skid should be included. PCV and SDV wll be installed
Note on I118: Olaniyi Afolabi: Pipe Support Location Plan should be deleted. The location of the pipe supports will be included in the GAD
Note on I121: Olaniyi Afolabi: This is a repetitive efforts. Piping Design Basis already captured
Note on I127: Olaniyi Afolabi: There is no provision for Piping Stress Analysis, Piping Critical Line List. Heater is a critical equipment and some attached lines must be stress analysed. Also make provisions for piping LLI
Note on I144: Olaniyi Afolabi: RFQ and TBE are not required since we shall not engage the vendors or OEM. Please make provision for Material Requisitions Only. Also delete deliverables related to the Slop Tank. It is an existin equipment
Note on I170: Olaniyi Afolabi: The Slop Tank is existing and should not be included
Note on I182: Olaniyi Afolabi: Please delete. The Slop Tank is existing according to the SoW