## Master Document Register
Doc Number | DOC Title | Category | Status | Due Date | Priority | Revision | Responsible Engineer | Description | Created Date | Last Updated | Client | Project Phase
PRJ-001 | Project Execution Plan | Project Management | In Progress | 2024-02-15 | High | Rev-1 | John Smith | Overall project execution strategy and timeline | 2024-01-15 | 2024-02-01 | XYZ Oil Corporation | Detailed Design
PRJ-002 | Risk Assessment Matrix | Project Management | Not Started | 2024-02-20 | High | Rev-0 | John Smith | Comprehensive project risk analysis | 2024-01-15 | 2024-02-01 | XYZ Oil Corporation | Detailed Design
PRJ-003 | Quality Assurance Plan | Project Management | Under Review | 2024-02-10 | Medium | Rev-1 | John Smith | QA procedures and standards | 2024-01-15 | 2024-02-01 | XYZ Oil Corporation | Detailed Design
PRJ-004 | Project Schedule | Project Management | Completed | 2024-01-25 | High | Rev-2 | John Smith | Master project timeline and milestones | 2024-01-15 | 2024-02-01 | XYZ Oil Corporation | Detailed Design
PRJ-005 | Communications Plan | Project Management | In Progress | 2024-02-12 | Low | Rev-1 | John Smith | Stakeholder communication strategy | 2024-01-15 | 2024-02-01 | XYZ Oil Corporation | Detailed Design
SAF-001 | HSE Management Plan | Safety | Approved | 2024-01-30 | High | Rev-2 | Sarah Wilson | Health Safety and Environment procedures | 2024-01-15 | 2024-02-01 | XYZ Oil Corporation | Detailed Design
SAF-002 | HAZOP Study Report | Safety | Under Review | 2024-02-18 | High | Rev-1 | Sarah Wilson | Hazard and operability analysis | 2024-01-15 | 2024-02-01 | XYZ Oil Corporation | Detailed Design
SAF-003 | Emergency Response Plan | Safety | In Progress | 2024-02-25 | High | Rev-1 | Sarah Wilson | Emergency procedures and evacuation plans | 2024-01-15 | 2024-02-01 | XYZ Oil Corporation | Detailed Design
SAF-004 | Fire Protection Design | Safety | Not Started | 2024-03-01 | High | Rev-0 | Sarah Wilson | Fire detection and suppression systems | 2024-01-15 | 2024-02-01 | XYZ Oil Corporation | Detailed Design
PRC-001 | Process Flow Diagram | Process | In Progress | 2024-02-25 | High | Rev-1 | Mike Johnson | Main process flow for distillation unit | 2024-01-15 | 2024-02-01 | XYZ Oil Corporation | Detailed Design
PRC-002 | Heat and Material Balance | Process | Not Started | 2024-03-01 | High | Rev-0 | Mike Johnson | Thermal and mass balance calculations | 2024-01-15 | 2024-02-01 | XYZ Oil Corporation | Detailed Design
PRC-003 | Process Control Philosophy | Process | In Progress | 2024-02-28 | Medium | Rev-1 | Mike Johnson | Control system design principles | 2024-01-15 | 2024-02-01 | XYZ Oil Corporation | Detailed Design
PRC-004 | Utility Requirements | Process | Under Review | 2024-02-18 | Medium | Rev-1 | Mike Johnson | Steam electricity and cooling water needs | 2024-01-15 | 2024-02-01 | XYZ Oil Corporation | Detailed Design
PRC-005 | Operating Manual | Process | Not Started | 2024-03-10 | Medium | Rev-0 | Mike Johnson | Detailed operating procedures | 2024-01-15 | 2024-02-01 | XYZ Oil Corporation | Detailed Design
PIP-001 | Piping and Instrumentation Diagram | Piping | In Progress | 2024-03-05 | High | Rev-1 | David Brown | P&ID for distillation section | 2024-01-15 | 2024-02-01 | XYZ Oil Corporation | Detailed Design
PIP-002 | Pipe Stress Analysis | Piping | Not Started | 2024-03-10 | High | Rev-0 | David Brown | Stress analysis for high temperature lines | 2024-01-15 | 2024-02-01 | XYZ Oil Corporation | Detailed Design
PIP-003 | Piping Material Specification | Piping | Under Review | 2024-02-22 | Medium | Rev-1 | David Brown | Material specs for all piping systems | 2024-01-15 | 2024-02-01 | XYZ Oil Corporation | Detailed Design
PIP-004 | Isometric Drawings | Piping | Not Started | 2024-03-15 | Medium | Rev-0 | David Brown | 3D piping layout drawings | 2024-01-15 | 2024-02-01 | XYZ Oil Corporation | Detailed Design
PIP-005 | Piping Support Design | Piping | In Progress | 2024-03-08 | Medium | Rev-1 | David Brown | Structural supports for piping systems | 2024-01-15 | 2024-02-01 | XYZ Oil Corporation | Detailed Design
INS-001 | Instrument Index | Instrumentation | In Progress | 2024-02-26 | High | Rev-1 | Lisa Chen | Complete list of all instruments | 2024-01-15 | 2024-02-01 | XYZ Oil Corporation | Detailed Design
INS-002 | Control System Architecture | Instrumentation | Not Started | 2024-03-02 | High | Rev-0 | Lisa Chen | DCS and safety system design | 2024-01-15 | 2024-02-01 | XYZ Oil Corporation | Detailed Design
INS-003 | Instrument Data Sheets | Instrumentation | In Progress | 2024-02-29 | Medium | Rev-1 | Lisa Chen | Detailed specs for all instruments | 2024-01-15 | 2024-02-01 | XYZ Oil Corporation | Detailed Design
INS-004 | Loop Diagrams | Instrumentation | Not Started | 2024-03-08 | Medium | Rev-0 | Lisa Chen | Control loop wiring diagrams | 2024-01-15 | 2024-02-01 | XYZ Oil Corporation | Detailed Design
INS-005 | Safety Instrumented System | Instrumentation | Under Review | 2024-02-20 | High | Rev-1 | Lisa Chen | SIS design and implementation | 2024-01-15 | 2024-02-01 | XYZ Oil Corporation | Detailed Design
ELE-001 | Electrical Load List | Electrical | In Progress | 2024-02-24 | High | Rev-1 | Robert Taylor | Power requirements for all equipment | 2024-01-15 | 2024-02-01 | XYZ Oil Corporation | Detailed Design
ELE-002 | Single Line Diagram | Electrical | Not Started | 2024-03-03 | High | Rev-0 | Robert Taylor | Main electrical distribution diagram | 2024-01-15 | 2024-02-01 | XYZ Oil Corporation | Detailed Design
ELE-003 | Motor Control Center Layout | Electrical | Under Review | 2024-02-27 | Medium | Rev-1 | Robert Taylor | MCC arrangement and specifications | 2024-01-15 | 2024-02-01 | XYZ Oil Corporation | Detailed Design
ELE-004 | Cable Schedule | Electrical | Not Started | 2024-03-12 | Medium | Rev-0 | Robert Taylor | Complete cable routing schedule | 2024-01-15 | 2024-02-01 | XYZ Oil Corporation | Detailed Design
ELE-005 | Grounding System Design | Electrical | In Progress | 2024-03-05 | High | Rev-1 | Robert Taylor | Plant grounding and lightning protection | 2024-01-15 | 2024-02-01 | XYZ Oil Corporation | Detailed Design
STR-001 | Structural Steel Drawings | Structural | In Progress | 2024-03-06 | High | Rev-1 | James Wilson | Steel structure for equipment support | 2024-01-15 | 2024-02-01 | XYZ Oil Corporation | Detailed Design
STR-002 | Foundation Design | Structural | Not Started | 2024-03-11 | High | Rev-0 | James Wilson | Concrete foundations for all equipment | 2024-01-15 | 2024-02-01 | XYZ Oil Corporation | Detailed Design
STR-003 | Wind Load Analysis | Structural | Under Review | 2024-02-23 | Medium | Rev-1 | James Wilson | Wind loading calculations for structures | 2024-01-15 | 2024-02-01 | XYZ Oil Corporation | Detailed Design
STR-004 | Seismic Analysis | Structural | Not Started | 2024-03-13 | Medium | Rev-0 | James Wilson | Earthquake resistance analysis | 2024-01-15 | 2024-02-01 | XYZ Oil Corporation | Detailed Design
CIV-001 | Site Plan | Civil | Approved | 2024-01-25 | High | Rev-2 | Emma Davis | Overall site layout and access roads | 2024-01-15 | 2024-02-01 | XYZ Oil Corporation | Detailed Design
CIV-002 | Grading and Drainage Plan | Civil | In Progress | 2024-02-21 | Medium | Rev-1 | Emma Davis | Surface water management system | 2024-01-15 | 2024-02-01 | XYZ Oil Corporation | Detailed Design
CIV-003 | Utility Routing Plan | Civil | Under Review | 2024-02-19 | Medium | Rev-1 | Emma Davis | Underground utility corridor layout | 2024-01-15 | 2024-02-01 | XYZ Oil Corporation | Detailed Design
CIV-004 | Paving and Roads Design | Civil | Not Started | 2024-03-07 | Low | Rev-0 | Emma Davis | Internal road system design | 2024-01-15 | 2024-02-01 | XYZ Oil Corporation | Detailed Design
MEC-001 | Equipment List | Mechanical | In Progress | 2024-02-16 | High | Rev-1 | Tom Anderson | Complete mechanical equipment inventory | 2024-01-15 | 2024-02-01 | XYZ Oil Corporation | Detailed Design
MEC-002 | Pump Data Sheets | Mechanical | Under Review | 2024-02-28 | High | Rev-1 | Tom Anderson | Specifications for all process pumps | 2024-01-15 | 2024-02-01 | XYZ Oil Corporation | Detailed Design
MEC-003 | Heat Exchanger Design | Mechanical | In Progress | 2024-03-04 | High | Rev-1 | Tom Anderson | Shell and tube heat exchanger specs | 2024-01-15 | 2024-02-01 | XYZ Oil Corporation | Detailed Design
MEC-004 | Compressor Specifications | Mechanical | Not Started | 2024-03-09 | Medium | Rev-0 | Tom Anderson | Process gas compressor requirements | 2024-01-15 | 2024-02-01 | XYZ Oil Corporation | Detailed Design
MEC-005 | Vessel Design Calculations | Mechanical | Under Review | 2024-02-26 | High | Rev-1 | Tom Anderson | Pressure vessel design and analysis | 2024-01-15 | 2024-02-01 | XYZ Oil Corporation | Detailed Design
ENV-001 | Environmental Impact Assessment | Environmental | Approved | 2024-01-20 | High | Rev-1 | Rachel Green | Environmental compliance documentation | 2024-01-15 | 2024-02-01 | XYZ Oil Corporation | Detailed Design
ENV-002 | Air Emissions Permit | Environmental | Under Review | 2024-02-17 | High | Rev-1 | Rachel Green | Air quality permit application | 2024-01-15 | 2024-02-01 | XYZ Oil Corporation | Detailed Design
ENV-003 | Waste Management Plan | Environmental | In Progress | 2024-02-25 | Medium | Rev-1 | Rachel Green | Solid and liquid waste disposal | 2024-01-15 | 2024-02-01 | XYZ Oil Corporation | Detailed Design
ENV-004 | Noise Impact Study | Environmental | Not Started | 2024-03-14 | Low | Rev-0 | Rachel Green | Community noise level assessment | 2024-01-15 | 2024-02-01 | XYZ Oil Corporation | Detailed Design

## Summary by Discipline
Discipline | Total Documents | Not Started | In Progress | Under Review | Approved | Completed
Project Management | 5 | 1 | 2 | 1 | 0 | 1
Safety | 4 | 1 | 1 | 1 | 1 | 0
Process | 5 | 2 | 2 | 1 | 0 | 0
Piping | 5 | 2 | 2 | 1 | 0 | 0
Instrumentation | 5 | 2 | 2 | 1 | 0 | 0
Electrical | 5 | 2 | 2 | 1 | 0 | 0
Structural | 4 | 2 | 1 | 1 | 0 | 0
Civil | 4 | 1 | 1 | 1 | 1 | 0
Mechanical | 5 | 1 | 2 | 2 | 0 | 0
Environmental | 4 | 1 | 1 | 1 | 1 | 0

## Project Information
Attribute | Value
Project Name | Oil Refinery Upgrade Phase 1
Client | XYZ Oil Corporation
Project Manager | John Smith
Start Date | 2024-01-15
Planned Completion | 2024-06-30
Total Documents | 46